## AHAR Timeline
AHAR Project Schedule |  |  | July 27 - July 29 | August 1 - August 31 | September 1 - September 30 | October 1 - October 31 | November 1 - November 30 | December 1 - December 31 | January 1, 2017 - January 31, 2017
| Person (s) | Task Completed
Provider Page Setup (Phase I)
Update provider pages to ensure correct program type | SO |  |  | 2016-08-04
Update provider pages to include Bed Counts | SO, AP |  |  | 2016-08-05
Update AHAR reporting group | SO |  |  | 2016-08-09
Ensure all provider zip codes are included in reporting group | SO |  |  | 2016-08-10
CoC Codes correct | SO |  |  | 2016-08-12
Geo Codes correct | SO |  |  | 2016-08-12
Data Quality (Phase II)
Send email to all providers to Generate UDE Report and clean up data | SO |  | 2016-07-29
Each Sys Admin Run UDE Completion Report 10/1/15 to 9/30/16 for each provider ensuring 100% completeness - Report to all Sys Admins | SO, KH, AA |  |  | August 3, 2016 August 19, 2016
Sys Admin report out on data quality - Meeting | SO, KH, AA |  |  | 2016-08-12
All data is cleaned up and there is 100% data completion for each project | AA's, SO, KH, AA |  |  | 2016-08-19
Service Transactions closed | AA's, SO, KH, AA |  |  |  | 2016-09-16
Entry/Exits closed - Length of Stay report [PATH & Outreach] | AA's, SO, KH, AA |  |  |  | 2016-09-18
Household data cleaned up | AA's, SO, KH, AA |  |  |  | 2016-09-30
Utilization Rate issues identified | AA's, SO, KH, AA |  |  |  | 2016-09-30
Draft AHAR Report Generation (Phase III)
Attend MCAH's AHAR training | SO |  |  |  |  | October 2016
Contact ABT Associates | SO |  |  |  |  | 2016-10-03
Share draft report with ABT Associates and get feedback | SO
Run CoC-wide AHAR report for each category; separate runs for All Persons and Veterans only. | SO |  |  |  |  | 2016-10-03
Re-run AHAR report for each AHAR reporting category and each program if necessary | SO |  |  |  |  | 2016-10-17
Upload Draft AHAR report to HDX | SO | [5 empty] | November 2016
Final AHAR Report Generation (Phase IV)
Upload final AHAR reports into HDX | SO | [6 empty] | December 2016
Update AHAR Guidebook to include all AHAR documents | SO | [7 empty] | January 2017
Printout AHAR published report and post to HAND website | SO | [7 empty] | January 2017

## HMIS Project Plan
AHAR Timeline
AHAR Project Schedule |  |  | July 27 - July 29 | August 1 - August 31 | September 1 - September 30 | October 1 - October 31 | November 1 - November 30 | December 1 - December 31 | January 1, 2017 - January 31, 2017
| Person (s) | Task Completed
Provider Page Setup (Phase I)
Update provider pages to ensure correct program type | SO |  |  | 2016-08-04
Update provider pages to include Bed Counts | SO, AP |  |  | 2016-08-05
Update AHAR reporting group | SO |  |  | 2016-08-09
Ensure all provider zip codes are included in reporting group | SO |  |  | 2016-08-10
CoC Codes correct | SO |  |  | 2016-08-12
Geo Codes correct | SO |  |  | 2016-08-12
Data Quality (Phase II)
Send email to all providers to Generate UDE Report and clean up data | SO |  | 2016-07-29
Each Sys Admin Run UDE Completion Report 10/1/15 to 9/30/16 for each provider ensuring 100% completeness - Report to all Sys Admins | SO, KH, AA |  |  | August 3, 2016 August 19, 2016
Sys Admin report out on data quality - Meeting | SO, KH, AA |  |  | 2016-08-12
All data is cleaned up and there is 100% data completion for each project | AA's, SO, KH, AA |  |  | 2016-08-19
Service Transactions closed | AA's, SO, KH, AA |  |  |  | 2016-09-16
Entry/Exits closed - Length of Stay report [PATH & Outreach] | AA's, SO, KH, AA |  |  |  | 2016-09-18
Household data cleaned up | AA's, SO, KH, AA |  |  |  | 2016-09-30
Utilization Rate issues identified | AA's, SO, KH, AA |  |  |  | 2016-09-30
Draft AHAR Report Generation (Phase III)
Attend MCAH's AHAR training | SO |  |  |  |  | October 2016
Contact ABT Associates | SO |  |  |  |  | 2016-10-03
Share draft report with ABT Associates and get feedback | SO
Run CoC-wide AHAR report for each category; separate runs for All Persons and Veterans only. | SO |  |  |  |  | 2016-10-03
Re-run AHAR report for each AHAR reporting category and each program if necessary | SO |  |  |  |  | 2016-10-17
Upload Draft AHAR report to HDX | SO | [5 empty] | November 2016
Present AHAR Draft to Data Committee and Board | SO
Final AHAR Report Generation (Phase IV)
Upload final AHAR reports into HDX | SO | [6 empty] | December 2016
Update AHAR Guidebook to include all AHAR documents | SO | [7 empty] | January 2017
Printout AHAR published report and post to HAND website | SO | [7 empty] | January 2017
Present Final AHAR to Data Committee and Board | SO